## README
Last Update | 2018-10-12
Author | Computing Carrots: Christian P, Joseph P, Philip K, Ryan W, Sean D
Email | sdoer001@ucr.edu, cpoma001@ucr.edu, jpark259@ucr.edu, pkawa001@ucr.edu, rwils006@ucr.edu
Description | This is a SCRUM template for our CS180 project: Scribble
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
7 | Account: creation | As an unregistered customer who is insterested in the app, I want to register an account so that I can login the app | 3 | 1
8 | Account: login | As a user I wiould like to be able to log in with my email and password | 100 | 2
3 | Events: create | As a user I would like to be able to create events | 8 | 3
2 | Events: view list | As a user I would like to be able to see a list of my events | 4 | 4 | To be split
4 | Events: view cal | As a user I would like to be able to see a calendar with my events | 2 | 5
6 | Account: g+ login | As a user I would like to be able to login with my google account | 6 | 6
5 | Account: fb login | As a user I would like to be able to log in with my facebook | 2 | 7
| Total |  | 125

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: Account Creation
Task 2: Account Login
Task 3: Event Creation
Task 4: Event view list
Task 5: Event view Calendar
Task 6: Login G+
Task 7: Login Facebook

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | David Hoffman | Task 1: Login Page Design (John Li)
1 | David Hoffman | Task ?
.. | .. | ..

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 35 | 0 | 0 | 35 | 35
1 | 35 | 2 | 2 | 33 | 30.625
2 | 36 | 3 | 5 | 31 | 26.25
3 | 36 | 3 | 8 | 28 | 21.875
4 | 36 | 4 | 12 | 24 | 17.5
5 | 34 | 3 | 15 | 19 | 13.125
6 |  |  |  |  | 8.75
7 |  |  |  |  | 4.375
8 |  |  |  |  | 0