## README
Last Update | 2018-10-12
Author | Computing Carrots: Christian P, Joseph P, Philip K, Ryan W, Sean D
Email | sdoer001@ucr.edu, cpoma001@ucr.edu, jpark259@ucr.edu, pkawa001@ucr.edu, rwils006@ucr.edu
Description | This is a SCRUM template for our CS180 project: Scribble
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
5 | Events: Geo locator | As a user I would like to be able to use geo-location to pinpoint where my event will be | 5 | 1
6 | Account: Validate user input | As a user I would like to have the correct data and details in my event | 15 | 2
7 | Account: Profile Creation | As a user I would like to be able to create a profile | 50 | 3
8 | Account: Contact Groups | As a user I would like to be able to put my contacts into groups | 40 | 4
9 | Account: Contact Add/Delete | As a user I would like to be able to add and delete contacts | 3 | 5
10 | Events: Notifications | As a user I would like to be able to see notifications of events | 1 | 6
11 | Events: Edit existing events | As a user I would like to be able to edit existing events | 8 | 7
| Total |  | 122

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: Account Creation | Done | Done | Done
Task 2: Account Login | Done | Done | Done
Task 3: Event Creation | Done | Done | Done
Task 4: Event view list | Done | Done | Done
Task 5: Geo locator | Done | Done | Done
Task 6: Validate user input | In Progress
Task 7: Profile Creation | Done | Done | Done
Task 8: Contact Groups | In Progress
Task 9: Contact Add/Delete | In Progress
Task 10: Cross compatability w/ mobile | Done | Done | Done
Task 11: Edit attendance in event | Done | Done | Done

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Sean Doerr | Task 1: Account Login
1 | Sean Doerr | Task 2: Account Creation
2 | Christian P | Task 3: Event Creation
2 | Christian P | Task 4: Event View List
3 | Philip K | Task 5: Geo Location
3 | Philip K | Task 7: Profile Creation
3 | Philip K | Task 10: Cross Compatability w/ Mobile

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 35 | 24 | 0 | 11 | 35
1 | 66 | 44 | 44 | 22 | 30.625
2 | 122 | 55 | 99 | 23 | 26.25